## Лист1
Planning a wedding in 9 months - Checklist
| WHAT TO DO |  | ASSIGNED TO | START DATE | END DATE | COMMENTS
| 1 | 9 months out
| 1.1 | Set a budget.
| 1.2 | Pick a date. Or for more venue options, pick a timeframe so you can be flexible if your venue is already booked on desired weekends.
| 1.3 | Find your venue.
| 1.4 | Hire all the key players: a planner, photographer, florist, and band.
| 1.5 | Reserve room blocks.
| 1.6 | Hire a graphic designer and get to work on your save-the-dates.
| 1.7 | Choose your wedding party.
| 1.8 | Start getting inspired. Research to help you decide what look you are going for.
| 1.9 | Go wedding dress shopping.
| 2 | 7-8 months out
| 2.1 | Find an officiant, or if you're having a friend do it, let them know so they can start preparing a meaningful ceremony.
| 2.2 | Choose your bridesmaids' dresses and think about what your groom and his guys will be wearing.
| 2.3 | Do a hair and makeup trial with your stylist.
| 2.4 | Begin planning the rehearsal dinner.
| 2.5 | Arrange transportation.
| 2.6 | Place your event rentals order.
| 2.7 | If it's a destination wedding, make your travel plans.
| 2.8 | Begin the design process on your wedding invitations.
| 2.9 | Research the policy for marriage licenses where you are getting married.
| 3 | 3-6 months out
| 3.1 | Order the wedding cake.
| 3.2 | Finalize all wedding attire.
| 3.3 | Address your invitations.
| 3.4 | Finalize welcome baskets or wedding favors.
| 3.5 | Begin designing your programs, signage, and other day-of paper materials.
| 3.6 | Think about what music you would like played for your ceremony processional and recessionaland your first dance.
| 4 | 2 months out
| 4.1 | Write your vows.
| 4.2 | Mail out your invitations with an RSVP due in one month.
| 4.3 | Arrange for a bridal lunch on the wedding day—it's a jam-packed day, so you want to make sure you eat.
| 4.4 | Finalize your wedding-day song choices.
| 5 | 1 month out
| 5.1 | RSVPs should be in—follow up with those guests who have not responded.
| 5.2 | Write escort cards and seating cards.
| 5.3 | Work on your seating chart (if you'll have one).
| 5.4 | Break in your bridal shoes.
| 5.5 | Pick up any day-of paper materials.
| 5.6 | Confirm your marriage license.
| 5.7 | Find a housesitter or petsitter for the days you are honeymooning.
| 6 | 1-2 weeks out
| 6.1 | Confirm details with all your vendors and tell them the final guest count so they can plan accordingly.
| 6.2 | Pick up your wedding dress.
| 6.3 | Prepare gratuity.
| 6.4 | Give a wedding timeline to your bridesmaids and groomsmen and review expectations with them.
| 6.5 | Pack your bags.
| 6.6 | Relax and prepare to enjoy your wedding day!